## FYRE
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Blockchain Developer | Token Contracts | FYRE | User Story #1: ERC-20 Token Implementation | - Implement ERC-20 Token Contract for FYRE | 8
Blockchain Developer | Token Contracts | FYRE | User Story #1: ERC-20 Token Implementation | - Add Minting, Burning, and Transferring Functions | 6
Blockchain Developer | Token Contracts | FYRE | User Story #1: ERC-20 Token Implementation | - Test Standard Token Operations | 6
Blockchain Developer | Token Contracts | FYRE | User Story #4: SHLD Interaction with FYRE | - Develop FYRE Conversion Functions for SHLD Purchase | 12
Blockchain Developer | Token Contracts | FYRE | User Story #4: SHLD Interaction with FYRE | - Implement FYRE to MANA Conversion Mechanism | 10
Blockchain Developer | Token Contracts | FYRE | User Story #4: SHLD Interaction with FYRE | - Define and Code Governance Rules for FYRE Usage | 8
Blockchain Developer | Token Contracts | FYRE | User Story #4: SHLD Interaction with FYRE | - User Interface Development for Conversion Processes | 12
Blockchain Developer | Token Contracts | FYRE | User Story #4: SHLD Interaction with FYRE | - Testing and Security Review | 8

## SHLD
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Blockchain Developer | Token Contracts | SHLD | User Story #1: NEAR NFT Implementation for SHLD | - Develop ERC-721 Contract for Non-Transferable SHLD | 10
Blockchain Developer | Token Contracts | SHLD | User Story #1: NEAR NFT Implementation for SHLD | - On-Chain Metadata Storage | 8
Blockchain Developer | Token Contracts | SHLD | User Story #1: NEAR NFT Implementation for SHLD | - Testing Non-Transferable NFT Features | 6
Blockchain Developer | Token Contracts | SHLD | User Story #2: Governance Voting for SHLD Holders | - Develop Governance Voting Smart Contracts | 12
Blockchain Developer | Token Contracts | SHLD | User Story #2: Governance Voting for SHLD Holders | - Integrate SHLD Voting into Governance | 10
Blockchain Developer | Token Contracts | SHLD | User Story #2: Governance Voting for SHLD Holders | - Testing Governance Voting Mechanism | 8
Blockchain Developer | Token Contracts | SHLD | User Story #3: Project Contribution Voting | - Develop Project Contribution Voting Contracts | 12
Blockchain Developer | Token Contracts | SHLD | User Story #3: Project Contribution Voting | - Integrate Voting with Project Budgets | 10
Blockchain Developer | Token Contracts | SHLD | User Story #3: Project Contribution Voting | - Testing Project Voting and Budget Approval | 8

## MANA
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Blockchain Developer | Token Contracts | MANA | User Story #1: MANA Token Lifecycle Starting as ERC-20 Token | - Implement ERC-20 Token Contract for MANA | 8
Blockchain Developer | Token Contracts | MANA | User Story #1: MANA Token Lifecycle Starting as ERC-20 Token | - Develop Contribution Mechanism | 10
Blockchain Developer | Token Contracts | MANA | User Story #1: MANA Token Lifecycle Starting as ERC-20 Token | - Transition from ERC-20 to ERC-1400 upon Contribution | 12
Blockchain Developer | Token Contracts | MANA | User Story #1: MANA Token Lifecycle Starting as ERC-20 Token | - Test ERC-20 to ERC-1400 Transition Workflow | 8
Blockchain Developer | Token Contracts | MANA | User Story #2: ERC-1400 MANA Token Implementation | - Develop ERC-1400 Contract for MANA | 12
Blockchain Developer | Token Contracts | MANA | User Story #2: ERC-1400 MANA Token Implementation | - Implement Divisibility and Partition Features | 10
Blockchain Developer | Token Contracts | MANA | User Story #2: ERC-1400 MANA Token Implementation | - Test ERC-1400 Token Functionality | 14
Blockchain Developer | Token Contracts | MANA | User Story #3: Governance and Project Voting | - Develop Voting Smart Contracts for MANA | 16
Blockchain Developer | Token Contracts | MANA | User Story #3: Governance and Project Voting | - Integrate MANA Voting into Cooperative Governance | 10
Blockchain Developer | Token Contracts | MANA | User Story #3: Governance and Project Voting | - Project Allocation Voting with MANA | 4
Blockchain Developer | Token Contracts | MANA | User Story #3: Governance and Project Voting | - Test Governance and Project Voting | 12

## mana effort hours
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Frontend Developer | Mana DApp | mana hour tracking | Log Hours Worked | Implement basic input fields | 4
Backend Developer | Mana DApp | mana hour tracking | Log Hours Worked | Store logged hours in a secure database | 4
Backend Developer | Mana DApp | mana hour tracking | Log Hours Worked | Ensure logged hours exported | 2
Blockchain Developer | Mana DApp | mana hour tracking | Log Hours Worked Proofs | Record proof of work (hours logged) on-chain | 6
Frontend Developer | Mana DApp | mana hour tracking | Display Allocated MANA Hours | Implement dashboard | 6
Backend Developer | Mana DApp | mana hour tracking | Display Allocated MANA Hours | Fetch data from the project manager's MANA sheet | 4
Blockchain Developer | Mana DApp | mana hour tracking | Display Allocated MANA Hours | Log final MANA allocation on-chain | 4
Backend Developer | Mana DApp | mana hour tracking | Generate Report for Project Manager | Develop report generation feature | 6
Backend Developer | Mana DApp | mana hour tracking | Generate Report for Project Manager | Display discrepancies | 4
Backend Developer | Mana DApp | mana hour tracking | Generate Report for Project Manager | Export report as spreadsheet/PDF | 2
Blockchain Developer | Mana DApp | mana hour tracking | Generate Report for Project Manager | Store final report on-chain | 4
Frontend Developer | Mana DApp | mana hour tracking | Basic Display for Effort Tracking | Create front-end display | 4
Backend Developer | Mana DApp | mana hour tracking | Basic Display for Effort Tracking | Compare tracked hours with allocated MANA | 4
Blockchain Developer | Mana DApp | mana hour tracking | Basic Display for Effort Tracking | Record final tracked hours on-chain | 4

## mana hours to mana
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Backend Developer | Mana DApp | mana algorithm | Setup Project MANA Allocation | Define total MANA allocation | 8 | 8
Blockchain Developer | Mana DApp | mana algorithm | Setup Project MANA Allocation | Record final allocation on-chain | 4
Backend Developer | Mana DApp | mana algorithm | Calculate Role-Based Multipliers | Calculate the weighted average pay rate | 4 | 4
Blockchain Developer | Mana DApp | mana algorithm | Calculate Role-Based Multipliers | Log final multiplier values on-chain | 2
Backend Developer | Mana DApp | mana algorithm | Log Hours Worked | Set up hour tracking | 6 | 6
Blockchain Developer | Mana DApp | mana algorithm | Log Hours Worked | Record logged hours on-chain | 4
Backend Developer | Mana DApp | mana algorithm | Calculate MANA Per Hour | Calculate MANA per hour | 4 | 4
Blockchain Developer | Mana DApp | mana algorithm | Calculate MANA Per Hour | Log MANA per hour on-chain | 2
Backend Developer | Mana DApp | mana algorithm | Conduct 360-Degree Peer Voting | Set up peer voting system | 12 | 12
Blockchain Developer | Mana DApp | mana algorithm | Conduct 360-Degree Peer Voting | Store peer voting results on-chain | 4
Backend Developer | Mana DApp | mana algorithm | Implement Confidence Interval | Set up confidence intervals | 8 | 8
Blockchain Developer | Mana DApp | mana algorithm | Implement Confidence Interval | Record confidence intervals on-chain | 4
Backend Developer | Mana DApp | mana algorithm | Apply Pay Rate Modifier | Apply pay rate modifier | 6 | 6
Blockchain Developer | Mana DApp | mana algorithm | Apply Pay Rate Modifier | Log pay rate modifications on-chain | 2
Backend Developer | Mana DApp | mana algorithm | Apply Stakeholder Multiplier | Create stakeholder evaluation rubric | 10 | 10
Blockchain Developer | Mana DApp | mana algorithm | Apply Stakeholder Multiplier | Log stakeholder evaluations on-chain | 2
Backend Developer | Mana DApp | mana algorithm | Implement Feedback System | Develop feedback system | 6 | 6
Blockchain Developer | Mana DApp | mana algorithm | Implement Feedback System | Store feedback on-chain | 2
Backend Developer | Mana DApp | mana algorithm | Apply Final Scaling | Apply final scaling | 4 | 4
Blockchain Developer | Mana DApp | mana algorithm | Apply Final Scaling | Log final scaling on-chain | 2

## MANA Governance
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Frontend Developer | Mana DApp | MANA Governance | Voting Mechanism | Implement voting UI | 8
Backend Developer | Mana DApp | MANA Governance | Voting Mechanism | Develop backend logic | 10
Blockchain Developer | Mana DApp | MANA Governance | Voting Mechanism | Implement voting on-chain | 6
Project Manager | Mana DApp | MANA Governance | Voting Mechanism | Test voting mechanism | 4 | 4
Frontend Developer | Mana DApp | MANA Governance | Proposal Submission | Create proposal submission form | 6
Backend Developer | Mana DApp | MANA Governance | Proposal Submission | Store/retrieve proposals | 6
Blockchain Developer | Mana DApp | MANA Governance | Proposal Submission | Record proposals on-chain | 4
Project Manager | Mana DApp | MANA Governance | Proposal Submission | Review submissions | 4 | 4
Backend Developer | Mana DApp | MANA Governance | Governance Voting Report Generation | Develop report generation | 6
Backend Developer | Mana DApp | MANA Governance | Governance Voting Report Generation | Export report | 4
Blockchain Developer | Mana DApp | MANA Governance | Governance Voting Report Generation | Store report on-chain | 4
Project Manager | Mana DApp | MANA Governance | Governance Voting Report Generation | Finalize report | 2 | 2
Frontend Developer | Mana DApp | MANA Governance | Displaying MANA Allocations | Create display for MANA allocations | 6
Backend Developer | Mana DApp | MANA Governance | Displaying MANA Allocations | Fetch MANA allocation data | 4
Blockchain Developer | Mana DApp | MANA Governance | Displaying MANA Allocations | Record MANA allocations on-chain | 4
Project Manager | Mana DApp | MANA Governance | Displaying MANA Allocations | Ensure accuracy of MANA allocations | 2 | 2
Frontend Developer | Mana DApp | MANA Governance | Project Governance Voting | Implement project governance UI | 6
Backend Developer | Mana DApp | MANA Governance | Project Governance Voting | Backend logic for project voting | 6
Blockchain Developer | Mana DApp | MANA Governance | Project Governance Voting | Record project voting on-chain | 4
Frontend Developer | Mana DApp | MANA Governance | MANA Hours-to-MANA Conversion | Implement conversion UI | 6
Backend Developer | Mana DApp | MANA Governance | MANA Hours-to-MANA Conversion | Backend logic for conversion | 6
Blockchain Developer | Mana DApp | MANA Governance | MANA Hours-to-MANA Conversion | Record conversion on-chain | 4
Frontend Developer | Mana DApp | MANA Governance | View Final MANA Results | Create results dashboard | 6
Backend Developer | Mana DApp | MANA Governance | View Final MANA Results | Fetch MANA results | 4
Blockchain Developer | Mana DApp | MANA Governance | View Final MANA Results | Log final project hours on-chain | 4

## VicTory Exchange
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Frontend Developer | Mana DApp | VicTory Exchange | FYRE Purchase Interface | Connect Wallet | 6
Frontend Developer | Mana DApp | VicTory Exchange | FYRE Purchase Interface | Create FYRE Purchase Interface | 12
Backend Developer | Mana DApp | VicTory Exchange | FYRE Purchase Interface | Display Token Prices and Supply Stats | 8
Backend Developer | Mana DApp | VicTory Exchange | SHLD Purchase Simulation | Check FYRE Balance | 6
Frontend Developer | Mana DApp | VicTory Exchange | SHLD Purchase Simulation | Create SHLD Purchase Interface | 10
Frontend Developer | Mana DApp | VicTory Exchange | SHLD Purchase Simulation | AI-Generated Customization for SHLD NFTs | 12
Frontend Developer | Mana DApp | VicTory Exchange | MANA Contribution Interface | Create MANA Contribution Interface | 8
Backend Developer | Mana DApp | VicTory Exchange | MANA Contribution Interface | Setup MANA Contribution API | 8
Frontend Developer | Mana DApp | VicTory Exchange | MANA to FYRE Conversion | Create MANA-to-FYRE Conversion Interface | 8
Backend Developer | Mana DApp | VicTory Exchange | MANA to FYRE Conversion | Setup Conversion Logic and API | 10
Frontend Developer | Mana DApp | VicTory Exchange | MANA Collateralization | Create Collateralization Interface for MANA | 8
Backend Developer | Mana DApp | VicTory Exchange | MANA Collateralization | Manage Collateralization Logic and API | 10
Frontend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Integrate Frontend Wallet and Purchase Logic | 8
Backend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Test and Finalize Backend APIs | 8
Frontend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Overall Integration Testing | 8
Backend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Test and Finalize Backend APIs | 8
Frontend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Test and Finalize Backend APIs | 8
Backend Developer | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Overall Integration Testing | 8
Project Manager | Mana DApp | VicTory Exchange | Frontend and Backend Integration | Overall Integration Testing | 6 | 6

## Project Management
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Project Manager | Project Management | Project Management | Generate Token Contract Plans | Create plans for FYRE, SHLD, MANA | 30 | 30
Project Manager | Project Management | Project Management | Generate MANA Dapp Plans | Create plan for mana effort tracking and governance system | 20 | 20
Project Manager | Project Management | Project Management | Generate mana hr to mana algo | Create Algorithm for mana hours to mana conversions | 10 | 10
Project Manager | Project Management | Project Management | Generate plan for mana hr to mana algo | Create plan for mana hours to mana conversion | 10 | 10

## Server-PM
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Project Manager | Project Management | Server | Backend Template | Create backend template for MANA Dapp | 20 | 20
Project Manager | Project Management | Server | Backend Template | Create backend template for Vicotry Dapp | 20 | 20
Project Manager | Project Management | Server | Depoy Taiga | Deploy Taiga on Server | 40 | 40

## Content
Role | Subproject | Epic | Story | Task | Estimated Hours | Budgeted | Actual Hours
Content Developer | Project Management | Content | Website Landing Page | Create website template | 10 | 10
Content Developer | Project Management | Content | Victory Dapp Pages (FYRE SHLD, MANA) | Create Victory Dapp Templates | 20 | 20
Content Developer | Project Management | Content | MANA Dapp Landing Page | Create Mana DApp Templates | 10 | 10
Content Developer | Project Management | Content | Website Content | Create website content | 40
Content Developer | Project Management | Content | UI/UX | Add UI/UX elements | 40